## Slide 1: Topology module : status and planning
B.Bauß, V.Büscher, A.Ebling$, W.Ji, U.Schäfer, A.Reiß, E.Simioni, S.Tapprogge, V.Wenzel

## Slide 2: The Topology Processor in its habitat
Topo Processor
Muons
Legacy electrical links
Cluster Processor
CMX
Phase 0
CTP
Core
Jet/Energy Processor
CMX
From PPr / nMCMs
6.4Gb/s fibre bundles
Fibre links

## Slide 3: Topology Processor
To provide a maximum of flexibility for applying topological trigger criteria
All Level-1 trigger signals in a single module
Allow to correlate all trigger object types within full solid angle
  e/m clusters, tau
  Jets
  Missing Energy
  Recently: muon signals in phase 0
Ample logic resources to run many algorithms in parallel
Option to run separate algorithms on more than one topology module in parallel

## Slide 4: Topo processor features
AdvancedTCA form factor
High input bandwidth (@ 6.4Gb/s line rate)
  Electrons, tau, jets, MET : 553 Gb/s
  Muons 267 Gb/s
  Total aggregate bandwidth 820 Gb/s
Low processing latency on real-time path
On-FPGA multi-gigabit links
High density 12-channel opto transceivers (10Gb/s)
Fibre bundles from CMX
Fibre bundle into CTP core
Prepared for phase 1: accept line rates above 6.4Gb/s from future processors (FEXes, muons)

## Slide 5: Topology Processor Schedule
2010
2011
2012
2013
2014
Technology Demonstrator (BLT)
Functional Demonstrator (GOLD)
Prototype
Installation
GOLD delivery
Production Completed
Production module
Production prototype

## Slide 6: Functional Demonstrator : “GOLD”
Input from the backplane (up to 72 fibres per bundle)
10Gb/s 12-channel o/e converters on mezzanine
High performance FPGAs (XC6VLX240T) with multiple 6.4Gb/s transceivers
Output from opto links on the front panel towards CTP

## Slide 7: GOLD : first tests and results
PCB partially assembled
Smoke test / boundary scan
Fibre loopback tests
Signal integrity (eye diagrams, eye scan)
Transceiver parameter optimisation
 Successful @ 6.4Gb/s, BER < 5e-16
Initial set of service- and algorithmic firmware exists
Latency optimisation:
  Used to be 7-8 ticks including MGTs
  Recently: n-input parallel sort tree (n*(n-1)/2) comparators  ~ 1 LHC bunch tick for full jet channel count

## Slide 8: GOLD : some current activites
Convert Gigabit links to LHC synchronous operation
TTCrx daughter
Jitter cleaner
Systematic tests on all electrooptical data paths
Look into multi-fibre connectors (MTP/MPO up to 72 fibres) / attenuation
Latency, latency, la….
TTCdec/TTCrx
TTC optical in

## Slide 9: Topology Processor Schedule
2010
2011
2012
2013
2014
Technology Demonstrator (BLT)
Functional Demonstrator (GOLD)
Prototype
Installation
GOLD delivery
Production Completed
Production module
Production prototype

## Slide 10: L1Topo prototype design
From CMX
To CTP
Fully ATCA compliant
Minimize FPGA count
2 * XC7V485T  XC7V690T
1 XC7K325T (C)
Short multi-gigabit traces
High-density mid- board o/e converters (miniPOD) on main board
No on-board electrical duplication of real-time signals
Require upstream duplication

## Slide 11: L1Topo : Milestones
Specifications for prototype under way:
30.05.2012 design review
29.09.2012 prototype layout finished
01.12.2012 production/assembly completed
Start preparations for final module production in parallel with prototype module tests. Make prototype module available for initial tests / commissioning @ P1
04/2013 prototype system tests at P1 finished
05/2013 PRR
08/2013 production finished
11/2013 start commissioning at P1
07/2014 commissioning finished

## Slide 12: Summary
TP functional demonstrator (GOLD):
Partially equipped and successfully tested
Data path between FPGA and o/e converters works
Parameters optimized at 6.4 Gb/s
Large bit-error free window
Further optimization on high speed link parameters and performance of algorithms in hardware ongoing
TP Prototype:
Design ready, schematic capture in progress
Preparing documents for the review (05/ 2012)
On schedule for installation during shutdown 13/14