## Slide 1: L1Topo PCB/assembly saga
Prototype
PCB production at company W
20 working days starting on 11.04.2013
  delay 13.05. --> 24.05.2013
  delay 24.05. --> 04.06.2013
assembly at company S 06.2013
lab test Mainz 07.2013
  JTAG Boundary Scan errors found…
assembly 2nd copy prototype at ProDesign
  trying… 01.2014
  micro vias not filled properly/uneven surface ! (explains issues with 1st copy)
  new PCB round W, 30 working days 01.2014
  PCB delivery 03.2014
  assembly at ProDesign <1wk 03.2014
  delivery 03.2014
  JTAG Boundary scan ok 03.2014  prototype successfully built !
Production module (ProDesign + X (PCB))
order out to ProDesign 09.2014
PCB delaminated during assembly 11.2014
baking PCB (spare) tested ok 11.2014
2nd copy assembled/delaminated 11.2014
redo PCBs 11.2014
assembly last week 12.2014
delivery 1st copy today, looks good, initial results next wk.