## Slide 1
L1Topo Firmware
Proc FPGA Development status
  Realtime data path 90%
    MGTs 100% / Under Test
Decoding of input TOBs 85%
    Baseline Algorithms 100%
  Readout path
    Data Merging 80%
    Packet creation 60%
    Register definitions 70%
    ROD interface 60%
  Control Under test
Control FPGA (v.2=7-series, v.3=UltraScale+)
  Ethernet / IPbus v.2 100% v.3 50%
  Board Monitoring (v.3) 50%
Status summary
  Redistribution of algorithms studied
  Interfaces successfully tested
  Control F/W activities on v.3 will resume once new Topo module is running w. mezzanine v.3 (Nov.)
Next steps
  Finalizing decoding of input TOBs
  Final integration Infrastructure, Algos, Readout
9th April 2019
Ian Brawn on behalf of TDAQ
Resource utilization: Topological Algorithms
Compare old and new distribution
Goal to distribute resource utilization evenly
Topo LUT utilization for the topological FPGAs
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 2: L1Topo Software, Documentation & Integration
Software
  Register map (XML) 50%
  Module Control Package 50%
  Calibration Database Tools ?????
  Connectivity Database Tools ?????
  SW-ROD Plugin ?????
  Diagnostics Tools 50%
  Monitoring Histograms 0%
  Test Vector Generation 0%
  Bit-wise simulation * %
Documentation
  User Manual 0%
  Data Formats 70% ?
  Algorithm Specification 80%
Integration
  eFEX 90 % jFEX 98 % gFEX 80 % CTP/MUCTPI 30 %
  DCS 0 %
  Hub/ROD TTC ?? %
  Hub/ROD readout ?? %
  FELIX 0 %
  SwROD 0 %
  TDAQ 0 %
  Note: L1Topo Software derived from jFEX. Please refer to jFEX status. We expect to have it migrate to Topo in 1st week of November. Fall-back: standalone control and monitoring tools.
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 3: STF Slice Tests
TREX–eFEX protocol test Not Done/ In progress / Done
TREX–gFEX protocol test Not Done/ In progress / Done
TREX–jFEX protocol test Not Done/ In progress / Done
eFEX–Topo protocol test Done +
gFEX–Topo protocol test Almost done *
jFEX–Topo protocol test Done
eFEX Readout RT data → ROD Not Done/ In progress / Done
gFEX Readout RT data → FELIX Not Done/ In progress / Done
jFEX Readout RT data → ROD Not Done/ In progress / Done
Topo Readout RT data → ROD In progress
TREX Readout RT data → FELIX Not Done/ In progress / Done
eFEX data → FELIX Not Done/ In progress / Done
jFEX/Topo data → FELIX Not Done
FELIX → SW ROD Not Done/ In progress / Done
Data extraction from SW ROD Not Done/ In progress / Done
Full eFEX readout path Not Done/ In progress / Done
Full jFEX readout path Not Done/ In progress / Done
Full Topo readout path Not Done/ In progress / Done
Full gFEX readout path Not Done/ In progress / Done
Full TREX readout path Not Done/ In progress / Done
eFEX–Topo–Readout test Not Done/ In progress / Done
gFEX–Topo–Readout test Not Done/ In progress / Done
jFEX–Topo–Readout test Not Done/ In progress / Done
TREX–eFEX–Readout test Not Done/ In progress / Done
TREX–gFEX–Readout test Not Done/ In progress / Done
TREX–jFEX–Readout test Not Done/ In progress / Done
TREX–eFEX–Topo Slice Not Done/ In progress / Done
TREX–gFEX–Topo Slice Not Done/ In progress / Done
TREX–jFEX–Topo Slice Not Done/ In progress / Done
Full Slice test Not Done/ In progress / Done
+: might wish to test for larger channel count, *: waiting for final agreement on exact CRC
Notes: Mark in Not Done, In Progress or Done,
Where “Done” means you don’t need to repeat any aspect of this test before moving to the next stage