## Slide 1: eFEX Firmware
Proc FPGA Development status
  IPBus 90%
  Infrastructure 70%
  Real Time path 60%
    MGTs Tested
    Synchronisation 70%
    e/ algorithm 70%
    Tau algorithm 40%
    Sorting 90%
  Readout path Under test
    TOB Flow Control 60%
    RAW Flow Control 80%
    Control FPGA interface 85%
  Control Tested
Control FPGA
  ROD Aurora interface 100%
  TTC Interface 100%
  Readout path
    Flow Control 30%
  Control 90%
Status summary
  Control FPGA Infrastructure completed
  Real Time Path Test – Two pFPGAs tested
  Readout Path – TOB 50% & RAW 70% tested
  ROD interface verified
Next steps
  Complete real-time path tests with 4 pFPGAs
  Complete readout tests for both TOB and calorimeter readout
  Bug fix generic IPBus mapping for all pFPGAs
Proc FPGA Utilisation
Control FPGA Utilisation
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 2: eFEX Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  LATOME/LAr xx%
  TREX/Tile xx%
  L1Topo xx%
  DCS xx%
  Hub/ROD TTC xx%
  Hub/ROD readout xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 3: jFEX Firmware
Proc FPGA Development status
  Real-time data path
    MGTs 100% / Under Test
    Jet, ET/MET, Pileup algorithm 100%
    Large-R Jet, Tau algorithm 70% (1st version implemented)
  Readout path
    Data Merging 90%
    Packet creation 80%
    Register definitions 80%
    ROD interface 60%
  Control Under test
Control FPGA
  Ethernet / IPbus Under test
  Board Monitoring Under test
Status summary / Recent news
  Significant improvement on the forward region…
  Integration is well-advanced…
Next steps
  Commission w/ ROD interface
  Commission w/ TREX, LATOME, L1Topo
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 4: jFEX Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  LATOME/LAr xx%
  TREX/Tile xx%
  L1Topo xx%
  DCS xx%
  Hub/ROD TTC xx%
  Hub/ROD readout xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 5: gFEX Firmware
Proc FPGA Development status
  Real time path Under test
    LAr/Tile Inputs Under test
    Synchronisation Under test
    Large-R jets algorithm Under test
    Global algorithms Under test
  Readout path Under test
    Flow Control N/A
    Control FPGA interface Under test
  Control Under test
Control FPGA
  Real time path 60%
  Synchronisation Under test
  Readout path
    Flow Control 60%
    FELIX interface Under test
  Control 50%
Status summary
  Testing taking place with gFEX  FELIX setup at BNL using dummy input data loaded into playback memories
Next step(s)
  Test algorithms on 107 events with simplified timing
  Incorporate realistic flow control into readout
  Incorporate forward region (|| > 2.4)
  Test readout with algorithmic (MC) data
Proc FPGA Utilisation
Latency Measurement: 280 MHz clock
Time label and description | Time (clks) | Time (ns)
T0 – output of skew compensation block | 0 | 0
T1 – output of gTower builder (calibr. gTowers) | 19 | 67.9
T2 – partial sum for neighbor calculated | 31 | 110.7
T3 – partial sum TX output | 36 | 128.6
T4 – partial sum RX input | 40 | 142.9
T5 – partial sum input to jet engine | 44 | 157.1
T6 – Large R jet sum output | 46 | 164.3
T7 – TOB_1 ready signal | 61 | 217.9
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 6: gFEX Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  LATOME/LAr xx%
  TREX/Tile xx%
  L1Topo xx%
  DCS xx%
  FELIX TTC xx%
  FELIX readout xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 7: L1Topo Firmware
Proc FPGA Development status
  Realtime data path 90%
    MGTs 100% / Under Test
    Decoding of input TOBs 75%
    Baseline Algorithms 100%
  Readout path
    Data Merging 80%
    Packet creation 60%
    Register definitions 70%
    ROD interface 40%
  Control Under test
Control FPGA
  Ethernet / IPbus Under test
  Board Monitoring Under test
Status summary
  Integration well advanced
  Submission deadline for new algorithms: 30.6.19
Next steps
  Finalizing decoding of input TOBs
  Commissioning of interfaces
Resource utilization: Multiplicity Topo
Use Topo1b, assume all 110 output bits are jets
40 × 2 bit and 10 × 3 bit jet multiplicities
Numbers of input jets: 64 Jets, 128 Jets and 256 Jets
Topo LUT utilisation for different jet implementations
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 8: L1Topo Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  eFEX xx%
  jFEX xx%
  gFEX xx%
  CTP xx%
  DCS xx%
  Hub/ROD TTC xx%
  Hub/ROD readout xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 9: Hub Firmware
Design Area 1
  Item 1
  Item 2
  …
Design Area 3
  Item 1
  Item 2
Status summary / Recent news
  …
  …
Next steps
  …
  …
Utilisation chart from Vivado, etc.
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 10: Hub Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  ROD xx%
  eFEX xx%
  jFEX xx%
  L1Topo xx%
  DCS xx%
  TTC xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 11: ROD Firmware
Backplane Interface Development status
  eFEX interface 80%
    Aurora (3 channels) Tested
    All channels 70%
    Readout/CTTC 80%
    Status Registers 60%
  jFEX interface
    Aurora 80%
    Bus width adapter 80%
    All channels 50%
    Status Registers 60%
    Testing in jfex shelf 10%
  Topo interface not started
Packet Processor
  TOB/xTOB packets
    Event building 80%
    All header/trailer fields 70%
    Control/Status registers 70%
    Debug Queue 10%
  Bulk Data Handling
    Specification 80%
    Design 50%
Status summary / Recent news [optional]
  1st HW test with eFEX packets complete
Next step(s)
  PRR, Bulk Data implementation, Debug Queue
eFEX-ROD FPGA Utilisation
jFEX-ROD FPGA Utilisation
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 12: ROD Software, Documentation & Integration
Software
  Register map (XML) xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  Hub xx%
  eFEX xx%
  jFEX xx%
  L1Topo xx%
  DCS xx%
  TTC xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 13: TREX Firmware (1)
PREDATOR FPGA (Kintex UltraScale) Development status
  Real-time path
    LVDS data reception Tested
    Autom. input delay scan 10%
    De-BCMUX-ing Tested
    Data formatting 40%
    Transmission to FEXes 40%
  Readout path
    G-Link formatting 80%
    Transmission to legacy ROD 30%
    Transmission to FELIX 30%
  Configuration, Control & Monitoring
    System monitoring (SYSMON) Tested
    Interface to VME (via PPM/ExtReM) Tested
    Interface to FireFly transc. (I2C master) Tested
    Interface to Zynq+ MPSoc (I2C slave) 20%
DINO FPGAs (4x Artix-7)
  Real-time path
    LVDS duplication Tested
    Transmission to CP & JEP Tested
    Routing to PREDATOR FPGA Tested
  Monitoring
    System monitoring (XADC) Tested
    Interface to VME/Zynq+ (I2C slave) To be tested
FPGA & MPSoC Utilisation (master/official releases only)
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 14: TREX Firmware (2)
ExtReM FPGA (Virtex-1000E, on PPM) Development status
  Readout path
    Remove G-Link formatting Tested
    Route TTC signals to PREDATOR Tested
  Configuration & Control (from VME)
    Interface to PREDATOR Tested
    Interface to Zynq+ To be tested
    Register model for PREDATOR Tested
    Register model for Zynq+ 80%
    I2C master interface to TREX 90%
Zynq+ MPSoC (from TREX pre-production only)
  Configuration, Control & Monitoring (PL)
    Interface to VME (via PPM/ExtReM) 70%
    Interface to PS Not started
    I2C master interf. (slow-control) 30%
    System monitoring (SYSMON) 30%
    Slow-ctrl data storage & analysis 30%
  Slow-control Monitoring (PS)
    JTAG master Not started
    OPC/UA server Not started
    Communication w/ DCS (Ethernet) Not started
Status summary
  Zynq+ MpSoC to be implemented on the TREX pre-production module (TREX v2; June19)
  Currently, main focus on finalising the implementation of the real-time interface to FEXes and of the readout interface to the legacy ROD
Next step(s)
  Test legacy real-time path to CP & JEP (CERN bat-104)
  Test legacy readout interface to legacy ROD (CERN bat-104)
  Test real-time interface to FEXes (CERN STF)
FPGA & MPSoC Utilisation (master/official releases only)
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 15: TREX Software, Documentation & Integration
Software
  Register map xx%
  Module Control Package xx%
  Calibration Database Tools xx%
  Connectivity Database Tools xx%
  SW-ROD Plugin xx%
  Diagnostics Tools xx%
  Monitoring Histograms xx%
  Test Vector Generation xx%
  Bit-wise simulation xx%
Documentation xx%
  User Manual xx%
  Data Formats xx%
  Algorithm Specification xx%
Integration
  PPM xx%
  eFEX xx%
  jFEX xx%
  gFEX xx%
  DCS xx%
  TTC xx%
  Legacy ROD xx%
  FELIX xx%
  SwROD xx%
  TDAQ xx%
Status Summary
  …
  …
Next Steps
  …
  …
Notes: Status:
If item is in development, make a rough estimate of how complete development is, and colour-code it:
0-30% = red
40-70% = amber
80-100% = green
Under test or tested (where applicable) means development is complete excepting minor debug, and testing is in progress/completed
Utilisation bar charts are clipped from Vivado

## Slide 16: STF Slice Tests
TREX–eFEX protocol test Not Done/ In progress / Done
TREX–gFEX protocol test Not Done/ In progress / Done
TREX–jFEX protocol test Not Done/ In progress / Done
eFEX–Topo protocol test Not Done/ In progress / Done
gFEX–Topo protocol test Not Done/ In progress / Done
jFEX–Topo protocol test Not Done/ In progress / Done
eFEX Readout RT data → ROD Not Done/ In progress / Done
gFEX Readout RT data → FELIX Not Done/ In progress / Done
jFEX Readout RT data → ROD Not Done/ In progress / Done
Topo Readout RT data → ROD Not Done/ In progress / Done
TREX Readout RT data → FELIX Not Done/ In progress / Done
eFEX data → FELIX Not Done/ In progress / Done
jFEX/Topo data → FELIX Not Done/ In progress / Done
FELIX → SW ROD Not Done/ In progress / Done
Data extraction from SW ROD Not Done/ In progress / Done
Full eFEX readout path Not Done/ In progress / Done
Full jFEX readout path Not Done/ In progress / Done
Full Topo readout path Not Done/ In progress / Done
Full gFEX readout path Not Done/ In progress / Done
Full TREX readout path Not Done/ In progress / Done
eFEX–Topo–Readout test Not Done/ In progress / Done
gFEX–Topo–Readout test Not Done/ In progress / Done
jFEX–Topo–Readout test Not Done/ In progress / Done
TREX–eFEX–Readout test Not Done/ In progress / Done
TREX–gFEX–Readout test Not Done/ In progress / Done
TREX–jFEX–Readout test Not Done/ In progress / Done
TREX–eFEX–Topo Slice Not Done/ In progress / Done
TREX–gFEX–Topo Slice Not Done/ In progress / Done
TREX–jFEX–Topo Slice Not Done/ In progress / Done
Full Slice test Not Done/ In progress / Done
Notes: Mark in Not Done, In Progress or Done,
Where “Done” means you don’t need to repeat any aspect of this test before moving to the next stage