## eFex
eFex |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-17 |  | 2020-04-23 | 2020-06-03
pFPGA
| IPBus | 90% | 90% | 90% |  | 90% | 90%
| Infrastructure | 70% | 70% | 80% |  | 85% | 85%
| Real-Time path | 60% | 60% | 60% |  | 70% | 70%
| MGTs |  |  | Tested
| synchonisation | 70% | 70% | 90% |  | 90% | 90%
| e/g algorithm | 70% | 70% | 80% |  | 85% | 85%
| Tau algorithm | 40% | 40% | 40% |  | 45% | 50%
| sorting | 90% | 90% | 90% |  | 90% | 90%
| TOB Merging | [5 empty] | 50%
Readout Path
| TOB flow control | 50% | 60% | 80% | 85% | 85% | 85%
| RAW flow control | 50% | 80% | 80% | 85% | 85% | 85%
| cFPGA interface | 80% | 85% | 85% | 90% | 90% | 90%
| Error Flags | [5 empty] | 30%
| Control |  |  | Tested
cFPGA
| ROD Aurora interface | 80% | 100% | 100% |  | 100% | 100%
| TTC interface | 70% | 100% | 100% |  | 100% | 100%
| Readout path |  |  |  |  | 60% | 60%
| flow control | 30% | 30% | 30% |  | 30% | 30%
| Control | 90% | 90% | 90% |  | 90% | 90%
Software
| Register map (XML) |  |  | 90% |  |  | 95%
| Module Control Package |  |  | 20% |  | 30% | 50%
| Calibration Database Tools |  |  | 10% |  | 20% | 30%
| Connectivity Database Tools |  |  | 20% |  | 30% | 40%
| SW-ROD Plugin |  |  | 0% |  | 20% | 20%
| Diagnostics Tools |  |  | 40% |  | 50% | 55%
| Monitoring Histograms |  |  | 0% |  | 0% | 0%
| Test Vector Generation |  |  | 50% |  | 60% | 60%
| Online bit-wise simulation |  |  | 20% |  | 40% | 50%
Documentation
| User Manual |  |  | 50% |  | 70%
| Data Formats |  |  | 90% |  | 90%
| Algorithm Specification |  |  | 50% |  | 70%
Integration
| LATOME/LAr |  |  | 25% |  | 50%
| TREX/Tile |  |  | 50% |  | 80%
| L1Topo |  |  | 50% |  | 80%
| DCS |  |  | 50% |  | 80%
| Hub/ROD TTC |  |  | 50% |  | 50%
| Hub/ROD readout |  |  | 50% |  | 80%
| FELIX |  |  | 10% |  | 80%
| SwROD |  |  | 10% |  | 10%
| TDAQ |  |  | 0% |  | 0%

## jFex
jFex |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  | 2019-06-27 | 2019-10-14 |  |  | 2020-06-02
pFPGA
| Real-Time Path | 80% | 80% |  |  | 85% | 95%
| MGTs | 95% | 100% | 100% |  | 100% | 100%
| Jet, Et/MET, Pileup algorithm | 100% | 100% | 100% |  | 100% | 100%
| Large-R Jet, Tau algorithm | 70% | 70% | 70% |  | 80% | 90%
| Readout Path | 40% |  |  |  | Processed
| Data merging |  | 90% | 90% |  | 90% | 90%
| Packet creation |  | 80% | 80% |  | 90% | 90%
| Register definition |  | 80% | 80% |  | 80% | 80%
| ROD interface |  | 60% | 60% |  | 90% | 90%
| Control | Test | Test | Test |  | Test
cFPGA |  | 95%
| Ethernet/IPBus |  | Test | 50% |  | 90% | 90%
| Board Monitoring |  | Test | 50% |  | 90% | 90%
Software
| Register map (XML) |  |  | 50% |  | 75% | 85%
| Module Control Package |  |  | 50% |  | 75% | 80%
| Calibration Database Tools |  |  | 0% |  | 0% | 20%
| Connectivity Database Tools |  |  | 0% |  | 0%
| SW-ROD Plugin |  |  | 0% |  | 0%
| Diagnostics Tools |  |  | 50% |  | 50% | 60%
| Monitoring Histograms |  |  | 0% |  | 0%
| Test Vector Generation |  |  | 0% |  | 10% | 10%
| Online bit-wise simulation |  |  | 20% |  | 20% | 20%
Documentation
| User Manual |  |  | 0% |  | 0% | 0%
| Data Formats |  |  | 90% |  | 90% | 90%
| Algorithm Specification |  |  | 90% |  | 90% | 95%
Integration
| LATOME/LAr |  |  | 50% |  | 90% | 90%
| TREX/Tile |  |  | 90% |  | 100% | 100%
| L1Topo |  |  | 98% |  | 98% | 98%
| DCS |  |  | 20% |  | 20% | 20%
| Hub/ROD TTC |  |  | 50% |  | 60% | 60%
| Hub/ROD readout |  |  | 50% |  | 60% | 60%
| FELIX |  |  | 0% |  | 0%
| SwROD |  |  | 0% |  | 10% | 10%
| TDAQ |  |  | 0% |  | 0%
Note on C7: >1st version implemented
Note on D7: !st Version impllemented

## gFex
gFex |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-16 |  |  | 2020-06-17
pFPGA
| Real-Time path | Test |  | Test |  |  | 80%
| LAr/Tile inputs | Test |  | Test |  |  | 90%
| Synchronisation | Test |  | Test |  |  | 90%
| Large-R jets algorithm | Test |  | Test |  |  | 60%
| Global algorithms | Test |  | Test |  |  | 80%
| Readout path | Test |  | Test |  |  | 80%
| Flow control | [5 empty] | 70%
| cFPGA interface | Test |  | Test |  |  | 90%
| Control | Test |  | Test |  |  | 75%
cFPGA
| Real-Time path | 60% |  | 80% |  |  | 90%
| Synchronisation | Test |  | Test |  |  | 90%
Readout path
| Flow control | 60% |  | 70% |  |  | 90%
| FELIX Interface | Test |  | Test |  |  | 90%
| Control | 50% |  | 60% |  |  | 75%
Software
| Register map (XML) |  |  | 25% |  |  | 75%
| Module Control Package |  |  | 25% |  |  | 25%
| Calibration Database Tools |  |  | 0% |  |  | 0%
| Connectivity Database Tools |  |  | 25% |  |  | 25%
| SW-ROD Plugin |  |  | 50% |  |  | 75%
| Diagnostics Tools |  |  | 25% |  |  | 50%
| Monitoring Histograms |  |  | 0% |  |  | 0%
| Test Vector Generation |  |  | 75% |  |  | 75%
| Online bit-wise simulation |  |  | 90% |  |  | 90%
Documentation
| User Manual |  |  | 40% |  |  | 75%
| Data Formats |  |  | 90% |  |  | 99%
| Algorithm Specification |  |  | 80% |  |  | 90%
Integration
| LATOME/LAr |  |  | 25% |  |  | 75%
| TREX/Tile |  |  | 0% |  |  | 75%
| L1Topo |  |  | 50% |  |  | 75%
| DCS |  |  | 60% |  |  | 80%
| FELIX TTC |  |  | 100% |  |  | 100%
| FELIX readout |  |  | 100% |  |  | 100%
| SwROD |  |  | 0% |  |  | 75%
| TDAQ |  |  | 25% |  |  | 25%

## L1Topo
L1Topo |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-14 |  |  | 2020-06-04
pFPGA
| Real-Time path | 80% | 90% | 90% |  | 95% | 95% | 95%
| MGTs | 95% | 100% | 100% |  | 100% | Tested | Tested* |  |  | * baseline version, upgrade under way.
| Decode input TOBs | 50% | 75% | 85% |  | 95% | 95% | 95%
| Baseline algorithms | 100% | 100% | 100% |  | 100% | 100% | 100%
| New algorithms |  |  |  |  | 45% | 55% | 65% |  |  | This figure can go up and down, dependent on incoming requests
Readout path
| Data merging | 90% | 80% | 80% |  | 80% | 80% | 80%
| Packet creatiom | 70% | 60% | 60% |  | 60% | 60% | 60%
| Register definitions | 75% | 70% | 70% |  | 70% | 70% | 70%
| ROD Interface | 40% | 40% | 60% |  | 60% | 60% | 60%
| Control |  | Test | Test |  | Test | Tested | Tested
cFPGA
| Ethernet/IPBus |  | Test | 50% |  | 90% | 90% | 90%
| Board Monitoring |  | Test | 50% |  | 90% | 90% | 90%
Software
| Register map (XML) |  |  | 50% |  | 70% | 75% | 75%
| Module Control Package |  |  | 50% |  | 70% | 75% | 75%
| Calibration Database Tools |  |  | ?? |  | ?? | ?? | ?? |  |  | calibration s/w exists, not so connection to database
| Connectivity Database Tools |  |  | ?? |  | ?? | ?? | ??
| SW-ROD Plugin |  |  | ?? |  | ?? | ?? | ??
| Diagnostics Tools |  |  | 50% |  | 50% | 50% | 50%
| Monitoring Histograms |  |  | 0% |  | 0% | 0% | 0%
| Test Vector Generation |  |  | 0% |  | 10% | 10% | 10%
| Online bit-wise simulation |  |  | ?? |  | ?? | ?? | ??
Documentation
| User Manual |  |  | 0% |  | 0% | 0% | 0%
| Data Formats |  |  | 70% |  | 70% | 70% | 70%
| Algorithm Specification |  |  | 80% |  | 80% | 80% | 80%
Integration
| eFex |  |  | 90% |  | 90% | 90% | 90%
| jFEx |  |  | 98% |  | 98% | 98% | 98%
| gFex |  |  | 80% |  | 90% | 90% | 90%
| CTP/MUCTPI |  |  | 30% |  | 30% | 30% | 30%
| DCS |  |  | 0% |  | 0% | 0% | 0%
| Hub/ROD TTC |  |  | ?? |  | ?? | ?? | ??
| Hub/ROD readout |  |  | ?? |  | ?? | ?? | ??
| FELIX |  |  | 0% |  | 0% | 0% | 0%
| SwROD |  |  | 0% |  | 0% | 0% | 0%
| TDAQ |  |  | 0% |  | 0% | 0% | 0%

## Hub
Hub |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-14 |  | 2020-04-04 | 2020-06-05
FPGA
| Reception of clock & TTC data |  |  | 95% |  | 95% | 95%
| IPBUS component |  |  | 95% |  | 95% | 95%
| Readout Ctrl Data from ROD |  |  | 85% |  | 90% | 90%
| Combined Data→FEX slots 3,4,5 + ROD |  |  | 100%
| Combined Data→all FEX slots + ROD |  |  | 75% |  | 80% | 80%
| Integrated IBERT |  |  | 75% |  | 90% | 90%
| Eye Scan controlled via registers |  |  |  |  | 90% | 90%
| Eye Scan controlled via JTAG |  |  |  |  | 90% | 90%
| L1A generator (Test patterns) |  |  | 75% |  | 90% | 90%
Documentation
| User Manual |  |  | 50% |  | 50% | 50%
| Data Formats |  |  | 50% |  | 50% | 50%
| Algorithm Specification |  |  | 0% |  | 0% | 0%
Integration
| eFex |  |  | 50% |  | 50% | 50%
| jFex |  |  | 50% |  | 50% | 50%
| L1Topo |  |  | 50% |  | 50% | 50%
| DCS |  |  | 50% |  | 50% | 50%
| TTC |  |  | 75% |  | 90% | 90%
| ROD |  |  | 75% |  | 75% | 75%
| FELIX |  |  | 0% |  | 0% | 0%
| SwROD |  |  | 0% |  | 0% | 0%
| TDAQ |  |  | 0% |  | 0% | 0%

## ROD
ROD |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  | 2019-06-25 | 2019-10-18
Backplace Interface
| eFex Interface | 70% | 80% | 80%
| Aurora (3 channels) | Tested | Tested | 90% |  | 90%
| All channels | 70% | 80% | 70% |  | 70%
| Readout/CTTC | 70% | 80% | 80% |  | 90%
| Status Registers | 5% | 70% | 75% |  | 80%
jFex Interface
| Aurora | 70% | 80% | 80% |  | 80%
| Bus width adapter | 80% | 90% | 80% |  | 90%
| All channels | 40% | 90% | 70% |  | 70%
| Status Registers | 5% | 70% | 75% |  | 80%
| Testing in jFex shelf | Not Started | 10% | 10% |  | 30%
| Topo Interface | Not Started
| Aurora |  | 80% | 80% |  | 90%
| Bus width adapter |  | 90% | 80% |  | 90%
| All channels |  | 90% | 70% |  | 70%
| Status Registers |  | 70% | 75% |  | 80%
| Testing in Topo shelf |  | 10% | 10% |  | 10%
Packet Processor
TOB/xTOB packets
| Event building | 80% | 80% | 80% |  | 90%
| All header/trailer fields | 50% | 70% | 70% |  | 90%
| Control/status registers | 5% | 20% | 70% |  | 80%
| Debug queue |  | 10% | 70% |  | 80%
| Busy Processing |  | 10% | 10% |  | 10%
| Multiprocessing |  | 10% | ?? |  | 10%
| Bulk data handling |  |  | 80%
| Specification | 40% | 80% |  |  | 100%
| Design | 10% | 70% |  |  | 80%
| Pipeline Re-work |  |  | 10% |  | 50%
Felix Interface
| Full Mode Interface |  | 90% |  |  | 90%
| Control/status registers |  | 10% |  |  | 80%
| Bulk outputs |  |  |  |  | 80%
Error Handling
Software
| Register map (XML) |  |  | 70% |  | 80%
| Module Control Package |  |  | 0% |  | 0%
| Calibration Database Tools |  |  | 0% |  | 0%
| Connectivity Database Tools |  |  | 0% |  | 0%
| SW-ROD Plugin |  |  | 0% |  | 0%
| Diagnostics Tools |  |  | 0% |  | 30%
| Monitoring Histograms |  |  | 0% |  | 0%
| Test Vector Generation |  |  | 0% |  | 10%
| Online bit-wise simulation |  |  | 0% |  | 0%
Documentation
| User Manual |  |  | 5% |  | 5%
| Data Formats |  |  | 20% |  | 50%
| Algorithm Specification |  |  | 20% |  | 20%
Integration
| eFex |  |  | 70% |  | 70%
| jFex |  |  | 10% |  | 10%
| L1Topo |  |  | 10% |  | 10%
| DCS |  |  | ??
| TTC |  |  | 70% |  | 70%
| Hub |  |  | 80% |  | 80%
| FELIX |  |  | 50% |  | 50%
| SwROD |  |  | 50% |  | 50%
| TDAQ |  |  | 20% |  | 20%
Note on E7: Middleton, Robin (STFC,RAL,PPD): Less than June as understanding of CRC handling is not so optimistic.

## TREX
TREX |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-14 |  | 2020-04-08
Predator FPGA
Real-time path
| LVDS data reception | Tested | Tested | Tested |  | 100% | 100%
| Auto input delay scan | 10% | 10% | 10% |  | 95% | 96%
| De-BCMUX-ing | Tested | Tested | Tested |  | 100% | 100%
| Data formatting | 10% | 40% | 70% |  | 95% | 95%
| Transmission to FEXes | 10% | 40% | 50% |  | 80% | 80%
Readout path
| G-Link formatting | 60% | 80% | 80% |  | 100% | 100%
| Trans. To legacy ROD | 10% | 30% | 50% |  | 80% | 80%
| Trans. To FELIX | Not Started | 30% | 50% |  | 100% | 100%
Config, Control & Monitoring
| System monitoring | Tested | Tested | Tested |  | 100% | 100%
| Interface to VME | Tested | Tested | Tested |  | 100% | 100%
| Interface to FireFly transc. | Tested | Tested | Tested |  | 100% | 100%
| Interface to Zync+ MPSoc | Not Started | 20% | To Be Tested |  | 80% | 90%
Dino FPGA
Real-time path
| LVDS duplication | Tested | Tested | Tested |  | 100% | 100%
| Trans. to CP & JEP | Tested | Tested | Tested |  | 50% | 50%
| Routing to Predator FPGA | Tested | Tested | Tested |  | 100% | 100%
Monitoring
| System monitoring (XADC) | Tested | Tested | Tested |  | 100% | 100%
| Interface to VME/Zync |  |  | To Be Tested |  | 100% | 100%
ExtReM FPGA
Readout path
| Remove G-Link formatting | Tested | Tested | Tested |  | 100% | 100%
| Route TTC Signals to Predator | Tested | Tested | Tested |  | 100% | 100%
Config. & Control
| Interface to Predator | Tested | Tested | Tested |  | 100% | 100%
| Interface to Zync | 10% |  | To Be Tested |  | 100% | 100%
| Predator register model | Tested | Tested | Tested |  | 100% | 100%
| Zync+ register model | 50% | 80% | To Be Tested |  | 90% | 92%
| I2C master interface to TREX | Tested | 90% | To Be Tested |  | 100% | 100%
Zync+ MPSoC
Config. Control & Monitoring
| Interfce to VME | 10% | 70% | To Be Tested |  | 100% | 100%
| Interface to PS | Not Started | Not Started | 10% |  | 90% | 95%
| I"C Master Interface | 10% | 30% | To Be Tested |  | 100% | 100%
| System Monitoring | Not Started | 30% | To Be Tested |  | 80% | 90%
| Slow-ctrl data storage & analysis | Not Started | 30% | 50% |  | 50% | 70%
Slow-control Monitoring
| JTAG master | Not Started | Not Started | Not Started |  | 50% | 100%
| OPC/UA server | Not Started | Not Started | Not Started |  | 10% | 10%
| Communication with DCS | Not Started | Not Started | Not Started |  | 0% | 0%
Software
| Register map (XML) |  |  | 50% |  | 90% | 90%
| Module Control Package |  |  | 5% |  | 70% | 70%
| Calibration Database Tools |  |  | 0% |  | N/A | N/A
| Connectivity Database Tools |  |  | 0% |  | N/A | N/A
| SW-ROD Plugin |  |  | 0% |  | 5% | 5%
| Diagnostics Tools |  |  | 80% |  | 95% | 96%
| Monitoring Histograms |  |  | 0% |  | N/A | N/A
| Test Vector Generation |  |  | 100% |  | 100% | 100%
| Online bit-wise simulation |  |  | 100% |  | 90% | 90%
Documentation
| User Manual |  |  | 50% |  | 50% | 60%
| Data Formats |  |  | 100% |  | 100% | 100%
| Algorithm Specification |  |  | 100% |  | 100% | 100%
Integration
| PPM |  |  | 80% |  | 100% | 100%
| eFex |  |  | 70% |  | 80% | 80%
| jFex |  |  | 70% |  | 90% | 90%
| gFex |  |  | 0% |  | 70% | 70%
| DCS |  |  | 0% |  | 0% | 0%
| TTC |  |  | 50% |  | 100% | 100%
| Legacy ROD |  |  | 0% |  | 10% | 10%
| Legacy CP & JEP |  |  |  |  | 50% | 50%
| FELIX |  |  | 0% |  | 80% | 80%
| SwROD |  |  | 0% |  | 10% | 10%
| TDAQ |  |  | 20% |  | 70% | 70%

## FOX
FOX |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
(updated)
Integration
LATOME/LAr
TREX/Tile
eFex
jFEx
gFex

## TopoFOX
TopoFOX |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
(updated)
Integration
L1Topo
CTP

## STF-Slices
STF-Slices |  | Q1-19 | Q2-19 | Q3-19 | Q4-19 | Q1-20 | Q2-20 | Q3-20 | Q4-20 | JIRAs | Comment
| (updated) |  |  | 2019-10-17
| TREX–eFEX protocol test |  |  | Done |  |  | In progress
| TREX–gFEX protocol test |  |  | Not done |  |  | In progress
| TREX–jFEX protocol test |  |  | Done |  |  | In progress
| eFEX–Topo protocol test |  |  | Done |  |  | In progress |  |  |  | Q2-20: Protocal modified to get rid of idle word
| gFEX–Topo protocol test |  |  | In progress |  |  | In progress |  |  |  | Q2-20: zync done; proc FPGA to do
| jFEX–Topo protocol test |  |  | Done |  |  | Done(?) |  |  |  | Q2-20: To recheck after e/gFEX; make sure nothing changed
| eFEX Readout RT data → ROD |  |  | In progress |  |  | Done
| gFEX Readout RT data → FELIX |  |  | Done |  |  | Done
| jFEX Readout RT data → ROD |  |  | In progress |  |  | In progress
| Topo Readout RT data → ROD |  |  | In progress |  |  | In progress
| TREX Readout RT data → FELIX |  |  | Not done |  |  | In progress |  |  |  | Q2-20: Done but would like to re-test with newer modules
| eFEX data → FELIX |  |  | In progress |  |  | In progress |  |  |  | Q2-20: Variable stability; need fibres sorting our first
| jFEX/Topo data → FELIX |  |  | Not done |  |  | not done
| FELIX → SW ROD |  |  | Not done |  |  | In progress |  |  |  | Q2-20: tested many times; 1 success for gFEX→...SW ROD
| Data extraction from SW ROD |  |  | Not done |  |  | In progress |  |  |  | Q2-20: Draft event viewer for eFEX written; untested
| Full eFEX readout path |  |  | Not done |  |  | not done
| Full jFEX readout path |  |  | In progress |  |  | In progress
| Full Topo readout path |  |  | Not done |  |  | not done
| Full gFEX readout path |  |  | In progress |  |  | In progress
| Full TREX readout path |  |  | Not done |  |  | not done
| eFEX–Topo–Readout test |  |  | Not done |  |  | not done
| gFEX–Topo–Readout test |  |  | In progress |  |  | In progress
| jFEX–Topo–Readout test |  |  | In progress |  |  | In progress
| TREX–eFEX–Readout test |  |  | Not done |  |  | not done
| TREX–gFEX–Readout test |  |  | Not done |  |  | not done
| TREX–jFEX–Readout test |  |  | In progress |  |  | In progress
| TREX–eFEX–Topo Slice |  |  | Not done |  |  | In progress |  |  |  | Q2-20: data captured on Topo from all FEXs for checking offline
| TREX–gFEX–Topo Slice |  |  | Not done |  |  | In progress |  |  |  | Q2-20: data captured on Topo from all FEXs for checking offline
| TREX–jFEX–Topo Slice |  |  | In progress |  |  | In progress |  |  |  | Q2-20: data captured on Topo from all FEXs for checking offline
| Full Slice test |  |  | Not done |  |  | not done